## Gap Assessment
Control ID | Trust Criteria | Control Description | Control Objective | Current Implementation | Compliance Status | Gap Identified | Risk Level | Recommendation | Owner | Target Date
CC6.1 | Security | Logical access control are implemented | Ensure only authorized users access systems | Username & Password only | Partial | No multi-factor authentication | High | Implement MFA across all systems | IT security team | 2026-06-01
CC7.2 | Security | System monitoring is implemented | Detect unauthorized activities | No centralized logging | No | Lack of monitoring tools | High | Implement SIEM solution | Security operations | 2026-07-01
CC8.1 | Confidentiality | Data is protected during transmission | Prevent unauthorized data exposure | HTTPS enabled | Yes | None | Low | Maintain current controls | IT team | N/A
CC6.2 | Security | User access reviewed periodically | Ensure access remains appropriate | No formal access review process | No | Access not reviewed | High | Implement quarterly access rewiews | IT security team | 2026-06-15
CC6.3 | Security | Role based access control (RBAC) is implemented | Limit access based on job roles | Basic access roles exist | Partial | Roles not clearly defined | Medium | Define and enforce RBAC policy | IT team | 2026-06-20
CC7.1 | Security | Security events and logged | Track system activities | Logs exist but not monitored | Partial | No log monitoring | High | Implement log monitoring tools | Security operations | 2026-07-05
CC7.3 | Security | Incident response plan established | Respond to security incidents effectively | No formal incident response plan | No | No incident handling process | High | Develop incident response policy | Risk & Compliance team | 2026-06-30
CC5.1 | Security | Security policies are defined | Establish governance framework | Some policies exists | Partial | Policies not comprehensive | Medium | Develop full security policy suite | GRC team | 2026-06-25
A1.1 | Availability | Systems are monitored for uptime | Ensure system availabilty | Basic uptime checks | Partial | No automated alerts | Medium | Implement monitoring tools with alerts | IT operations | 2026-07-10
C1.1 | Confidentiality | Data encryption is implemented | Protect sensitive data | Encryption at rest only | Partial | No encryption in transit | High | Enable encryption in transit (TLS) | IT security | 2026-06-18
P1.1 | Privacy | Personal data is handled per regulations | Protect user privacy | No formal privacy policy | No | Lack of privacy framework | High | Develop privacy policy | Legal/Compliance | 2026-07-15